## Basic Gantt Chart
TASK NAME | START DATE | END DATE | START ON DAY | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE
Sprint 1
Project Description Document | 2020-02-15 | 2021-05-03 | THURSDAY | 10 | Aleks | 100%
Create A Git Repository | 2020-02-15 | 2021-05-03 | THURSDAY | 10 | Aleks | 100%
3 API GET operations | 2020-02-15 | 2021-05-03 | THURSDAY | 10 | Aleks | 100%
Project Plan Document | 2020-02-15 | 2021-05-03 | THURSDAY | 10 | Aleks | 100%
Sprint 2
Design Document | 2021-03-10 | 2021-03-26 | WEDNESDAY | 0 | Aleks | 0%
Implement database | 2021-03-10 | 2021-03-26 | WEDNESDAY | 0 | Aleks | 0%
Project Plan | 2021-03-10 | 2021-03-26 | WEDNESDAY | 0 | Aleks | 0%
Connection with frontend | 2021-03-10 | 2021-03-26 | WEDNESDAY | 0 | Aleks | 0%
Sprint 3
Project Plan | 2021-03-29 | 2021-04-19 | MONDAY | 0 | Aleks | 0%
Login frontend | 2021-03-29 | 2021-04-19 | MONDAY | 0 | Aleks | 0%
Register frontend | 2021-03-29 | 2021-04-19 | MONDAY | 0 | Aleks | 0%
Sprint 4
Home backend | 2021-04-20 | 2021-05-19 | MONDAY | 0 | Aleks | 0%
Project Plan | 2021-04-20 | 2021-05-19 | MONDAY | 0 | Aleks | 0%
Home frontend | 2021-03-29 | 2021-04-19 | MONDAY | 0 | Aleks | 0%
Sprint 5
Settings Page | 2021-05-21 | 2021-06-04 | WEDNESDAY | 0 | Aleks | 0%
Project Plan | 2021-05-21 | 2021-06-04 | WEDNESDAY | 0 | Aleks | 0%
Sprint 6
Final touches | 2021-06-06 | 2021-06-20 | MONDAY | 0 | Aleks | 0%

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 2 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 4 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 3 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 2 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 4 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 4 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 8 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 4 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 4 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 4 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 3 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 4 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 2 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 4 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 3 | Rachel | 40%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])